## Go Live for Loreal
Week 0 and 1 | 26th to 2nd Sept
LRN | Dates | Owner | Status | Remark
4th Dashboard | 26th Aug | Ram | Done - Technical testing | to open for beta testing
2nd Dashboard | 29th Aug | Ram | Done | 1 bug to solve
3rd Dashboard | 29th Aug | Ram | Done | to open beta testing
RLS Implementation | 29th to 2nd | Vinoth | In Progress | discussion about aggregate vs detailed (where RLS applied) + if it is applied on SF its applied on all dashboards /!\
Bug Fixes | 31st to 2nd | LTI | In Progress | [29-8]Ongoing
creation of YML, Parameterization on PowerBI dashboards, etc | 31st to 2nd | LTI | Done | AccountName, WH, Role and DB names [1-9]Only Dashboard 1 is remaining. YML is created for NP
Paginated (Detailed Report for dashboard 2 and dashboard 3) | 30th to 2nd | Ram | In Progress | Suryesh to contact MS for opinion and expertise
Mobile Friendly ? | 30th to 2nd | Ram | In Progress
Week 0 and 1 | 26th to 2nd Sept
PMGM | Dates | Owner | Status | Remark
Development finalization | 26th Aug | Swathi/Raja | Done | [29-8]Completed DBT dev. Minor changes in View remaining and adding the columns in the report [1-9]Dim Org vw is remaining
QA Deployment | 29th,30th | Mahesh/Swathi/Raja | Done | Will start picking this up today [1-9]Will be completed today
Fake data creation for Publish layer | 26th to 29th Aug | Pavani | Done | [29-8]Should be completed in 1st half today
Bug Fixes and Sprint 2 Development | 31st to 2nd | Swathi/Raja/Pavani/Mahesh | In Progress | Current Issue Employee Goals API extraction. Its not a blocker anyways. DBT development can continue
Week 0 and 1 | 26th to 2nd Sept
Common Tasks(NP and PD) | Dates | Owner | Status | Remark
Data Pipelines, and SFTP files movement(Existing files - from 30th June) | 26th to 31th | Chetan/Mahesh/Vinoth | Done
Setup Snowflake Environment | 29th | Suryesh/Sagar/Vinoth | Done
Adhoc run to copy the files from SFTP to DBT Core | 30th and 31st | Chetan/Mahesh/Vinoth | In Progress
Data Source Update - PA changes | 29th to 2nd Sept | Chetan/Mahesh | In progress | Problem Solved
Schedule LRN and PMGM on NP | 1st and 2nd Sept | Chetan/Mahesh/Vinoth/Swathi | Done | LRN OK and now PMGM
Week 2 | 5th to 9th Sept
Common Tasks | Dates | Owner | Status | Remark
Move to PD Environment - PMG and LRN | 5th Sept | Chetan/Mahesh/Vinoth | In Progress | 14th Learning & PMGM to be scheduled
Adhoc run to move the data | 5th Sept | Chetan/Mahesh/Vinoth | In Progress | 14th Learning & PMGM to be scheduled
Schedule LRN and PMGM on PD | 6th to 9th Sept | Chetan/Mahesh/Vinoth/Swathi | In Progress | 14th Learning & PMGM to be scheduled
Reload LRN Dev with Prod data |  |  | In Progress | 14th Learning & PMGM to be scheduled
Week 3 | 12th
Common Task | Dates | Owner | Status | Remark
Monitoring and Audit | To be scheduled
CICD | To be scheduled

## Tasks till 19th Sept
Tasks | Owner | Completion Date | Status | Remark | Priority Tasks
GCP
Stop the job if Key files empty | Mahesh | 15-09 | Done | Not Started, then will be completed by monday Developed and Testing completes.Needs to be move other env. | Y
Connect to data services and update the timestamp at the end of every job | Chetan | 16-09 | In Progress/ | In progress will be completed by monday 19/09: 402 error. Anas is investigating | Y
CICD implementation | Chetan/Mahesh | 16-09 | Done | In progress will be completed by monday 19/09: Implementation strategy has been changed after discussion with Kannan. ETA by today 5 PM. | Y
Move LRN code to Prod | Chetan/Vinoth | 19-09 | Done | Delayed by 1 day.
Schedule the Prod run for 20-09 | Mahesh/Vinoth | 19-09 | Inprogress | 19/09: Delayed by 1 day. Awaiting Snowflake stages to be created on prod to run the job for Full load,history & delta.
Monitor PMGM jobs and make it robust in all the 3 env | Chetan/Swathi | 15-09 to 19-09 | 16 th run succesful 19 th run successful | In progress | Y
Goal_3 API development. SFTP: XLS to CSV converstion integration in GCP job | Chetan/Mahesh | 16-09 | In Progress | In progress will be completed by monday 19/09: Development completed and testing in progress | Y
DBT
New development on Is Player (rising player and Future Leader) | Vinoth | 2022-09-19 |  | Discussion with Suryesh & Anas 19/09: Needs to add two columns in the existing snapshot tables. It will be completed by 20-09
New development on Assignment Profile Flag | Vinod | 15-09 |  | Done | Y
Validate RLS for Fact Table on Learning Add Ram's name and UPN with EMP as Suryesh and then ask ram to refresh all the views and see how it works.. Also, alter Policy and remove the 1st select query before we test this in Dev | Vinoth | 16-09 |  | Done
PMGM Sprint 2 development | Swathi/Pavani | 2022-09-19 | Done | Sprint 2 development completed- Need to review with Wael | Y
PowerBI
Paginated reports -Basic report | Ram | 16-09 to 19-09 |  | In progress, 19/09: Sent our analysis to Anas, Waiting for the reply. | Y
Bug fixes 3rd and 4th Dashboard(1 Fix open for 4th Dashboard) | Ram/Vinoth | 16-09 |  | 19/09: count is getting difference in QA and DV for 3rd dashboard. Need to work by tomorrow. for 4th dashboard, it is dependent on row no 12
PMGM Dashboard 2 - Missing KPI | Raja | 15-09 |  | completed, and it published. Wael has some point to add in it | Y
PMGM Dashboard 1 - Mobile report | Raja | 15-09 to 19-09 | Hold | 19/09: As discussed with wael, it has stopped until further notice | Y
PMGM Dashboard 1 - Follow up details report | Raja | 2022-09-19 | In progress | Assigned by Wael
Testing
Delta testing on PMGM | Lokesh | 16-09 |  | Completed
LRN Dashboard 3 | Lokesh | 19-09 |  | In progress | Y
LRN Dashbaord 4 | Lokesh | 21-09 |  | In progress

## Sheet1
Mahesh
Chetan
Vinoth
Swathi
Vinod
Pavani
Ram
Raja
Lokesh